## Sheet1
WBS | Name | Notes | Template Start_Date | Template Finish_Date | Duration | Predecessors | Planned Start_Date | Planned Finish_Date | Assignment | Formulae | Day Start | Day End | Project Start Date
1 | Phase 1 - Read the release notes and plan your upgrade | Phase 1 - Read the release notes and plan your upgrade... | 2019-02-07 08:00 | 2019-02-12 17:00 | 4 |  | 2024-04-03 | 2024-07-03 |  |  | 0:00 | 0:00 | 2024-04-03
1.1 | Review upgrade best practices | Review the upgrade best practices available at https://www.servicenow.com/upgrades The upgrade guide and best practices provides additional context and information that will help ensure a successful upgrade. | 2019-02-07 08:00 | 2019-02-07 17:00 | 1 |  | 2024-04-03 | 2024-04-03
1.2 | Review release notes | Review the release notes for the target ServiceNow feature release and patch as well as previous feature releases that may have been skipped. For example, if upgrading from Kingston to Madrid, be sure to read the London and Madrid release notes. Personalized release notes are provided as part of the Jumpstart your upgrade program. Release notes can also be found at https://docs.servicenow.com/ For specific upgrade considerations, see Upgrade and migration tasks by application or feature. | 2019-02-08 08:00 | 2019-02-12 17:00 | 3 | 2 | 2024-05-03 | 2024-07-03
1.3 | Review the supported web browsers to determine browser prerequisites | Review the supported web browsers to determine browser prerequisites. For example, versions and types supported, and additional requirements for new UI versions. Compare these supported browsers to your corporate standard and identify any gaps. | 2019-02-07 08:00 | 2019-02-07 17:00 | 1 |  | 2024-04-03 | 2024-04-03
2 | Phase 2 - Prepare for the development instance upgrade | Phase 2 - Prepare for the development instance upgrade... | 2019-02-13 08:00 | 2019-02-18 17:00 | 4 | 1 | 2024-08-03 | 13-03-2024 00:00
2.1 | Confirm which ServiceNow instances are in-scope for upgrade. | Confirm which ServiceNow instances are in-scope for upgrade. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.2 | Confirm the instance hosting model | Confirm the instance hosting model. For example, ServiceNow cloud, on-premise, or off-premise. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.3 | Determine new functionality or notable changes that need to be validated after the upgrade. | Based on the reviewed release notes and other release materials, determine new functionality or notable changes that need to be validated after the upgrade. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.4 | Confirm plans to enable or disable features introduced in the new product release. | Confirm plans to enable or disable features introduced in the new product release. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.5 | Create a project plan for cloning, upgrading, and testing. | Create a project plan for cloning, upgrading, and testing. | 2019-02-14 08:00 | 2019-02-14 17:00 | 1 | 8,7 | 2024-09-03 | 2024-09-03
2.6 | Identify core team of testers, power users, and key stakeholders required to validate functionality in the ServiceNow instances before and after the upgrade. | Identify the core team of testers, power users, and key stakeholders required to validate functionality in the ServiceNow instances before and after the upgrade. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.7 | Confirm any change freeze windows impacting the timing for environment clones or upgrades | Confirm whether there are any change freeze windows impacting the timing for environment clones or upgrades. For example, end quarter. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.8 | Confirm impact of non-production instance upgrade to development and testing | Confirm which of the following situations applies to your ServiceNow non-production instances:... | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.9 | Confirm the availability of other systems required for integration testing (key resources and environments). | Confirm the availability of other systems required for integration testing (key resources and environments). | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.1 | Confirm any restrictions in which ServiceNow instances can be used for integration testing | Confirm whether there are any restrictions in which ServiceNow instances can be used for integration testing. For example, an interfacing system is only set up to access a specific ServiceNow test instance. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.11 | Confirm the testing scope and approach | Confirm the testing scope and approach. | 2019-02-15 08:00 | 2019-02-15 17:00 | 1 | 10 | 2024-10-03 | 2024-10-03
2.12 | Create a comprehensive test plan including test cases for all core instance functionality and integrations. | Create a comprehensive test plan including test cases for all core instance functionality and integrations. | 2019-02-18 08:00 | 2019-02-18 17:00 | 1 | 16 | 2024-11-03 | 2024-11-03
2.13 | Confirm the method for tracking any defects identified during testing. | Confirm the method for tracking any defects identified during testing. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.14 | Create a high-level implementation plan | Create a high-level implementation plan that covers:... | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.15 | Confirm any change freeze windows impacting the timing for environment clones or upgrades | Confirm whether there are any change freeze windows impacting the timing for environment clones or upgrades. For example, end quarter. | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.16 | Determine whether existing internal training materials, Knowledge Base articles in the customer instance, or other supporting documentation must be updated to a | Determine whether existing internal training materials, Knowledge Base articles in the customer instance, or other supporting documentation must be updated to align with the upgraded version. For example, changes in functionality or user interface. | 2019-02-14 08:00 | 2019-02-14 17:00 | 1 | 7,8 | 2024-09-03 | 2024-09-03
2.17 | Optional: Schedule the ServiceNow Configuration Review, which provides recommendations to align the customer configurations with ServiceNow best practices. | Optional: Schedule the ServiceNow Configuration Review, which provides recommendations to align the customer configurations with ServiceNow best practices.... | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.18 | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance | 2019-02-13 08:00 | 2019-02-13 17:00 | 1 |  | 2024-08-03 | 2024-08-03
2.19 | Create a system clone of your production instance and select your development instance as the Target instance | On your production instance, create a system clone and select your development instance as the Target instance. Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the non-production inst | 2019-02-14 08:00 | 2019-02-14 17:00 | 1 | 19 | 2024-09-03 | 2024-09-03
3 | Phase 3 - Verify your upgrade configurations and schedule the development instance upgrade in HI | Phase 3 - Verify your upgrade configurations and schedule the development instance upgrade in HI... | 2019-02-19 08:00 | 2019-02-20 17:00 | 2 | 5 | 14-03-2024 00:00 | 15-03-2024 00:00
3.1 | Check the configuration of the Upgrade scheduled job to view how often and when it runs | Check the configuration of the Upgrade scheduled job to view how often and when it runs. | 2019-02-19 08:00 | 2019-02-19 17:00 | 1 |  | 14-03-2024 00:00 | 14-03-2024 00:00
3.2 | Verify that the Upgrade sys_trigger is set properly for upgrading | Verify that the Upgrade sys_trigger is set properly for upgrading. | 2019-02-19 08:00 | 2019-02-19 17:00 | 1 |  | 14-03-2024 00:00 | 14-03-2024 00:00
3.3 | Verify that the Check Upgrade Script sys_trigger is set properly for upgrading | Verify that the Check Upgrade Script sys_trigger is set properly for upgrading. | 2019-02-19 08:00 | 2019-02-19 17:00 | 1 |  | 14-03-2024 00:00 | 14-03-2024 00:00
3.4 | If applicable, request a version entitlement. | If applicable, request a version entitlement. | 2019-02-19 08:00 | 2019-02-19 17:00 | 1 |  | 14-03-2024 00:00 | 14-03-2024 00:00
3.5 | Schedule the upgrade in HI | Schedule the upgrade in HI. | 2019-02-20 08:00 | 2019-02-20 17:00 | 1 | 28,26,27 | 15-03-2024 00:00 | 15-03-2024 00:00
4 | Phase 4 - Upgrade and validate the development instance | Phase 4 - Upgrade and validate the development instance... | 2019-02-21 08:00 | 2019-02-28 17:00 | 6 | 25 | 18-03-2024 00:00 | 25-03-2024 00:00
4.1 | DEV: Using the Upgrade Monitor, monitor the upgrade; validate upgrade is complete. | Using the Upgrade Monitor, monitor the upgrade to your instance and validate that the upgrade to your development instance is complete. | 2019-02-21 08:00 | 2019-02-21 17:00 | 1 | 30,17 | 16-03-2024 00:00 | 16-03-2024 00:00
4.2 | DEV: Process skipped records list in the Upgrade Monitor. | After the upgrade for your development instance is complete, process the skipped records list in the Upgrade Monitor. | 2019-02-22 08:00 | 2019-02-26 17:00 | 3 | 32 | 17-03-2024 00:00 | 19-03-2024 00:00
4.3 | DEV: Identify update sets | Identify your update sets. | 2019-02-21 08:00 | 2019-02-21 17:00 | 1 |  | 18-03-2024 00:00 | 18-03-2024 00:00
4.4 | DEV: Before and after upgrading, conduct smoke tests | Before and after upgrading, conduct smoke tests on your development instance. Use your comprehensive test plan to perform functional testing. | 2019-02-27 08:00 | 2019-02-28 17:00 | 2 | 33,32 | 20-03-2024 00:00 | 21-03-2024 00:00
5 | Phase 5 - If applicable: Upgrade and validate your other non-production instances, such as your test instance | Phase 5 - If applicable: Upgrade and validate your other non-production instances, such as your test instance... | 2019-02-18 08:00 | 2019-03-22 17:00 | 25 | 31 | 26-03-2024 00:00 | 29-04-2024 00:00
5.1 | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance... | 2019-03-01 08:00 | 2019-03-01 17:00 | 1 |  | 26-03-2024 00:00 | 26-03-2024 00:00
5.2 | NON-PROD: Create a system clone from Prod and select the applicable NON-PROD instance as the Target instance | On your production instance, create a system clone and select your development instance as the Target instance. | 2019-03-01 08:00 | 2019-03-01 17:00 | 1 | 35 | 22-03-2024 00:00 | 22-03-2024 00:00
5.3 | NON-PROD: Before upgrade, run Automated Tests | Before executing the upgrade, Automated tests should be run to establish a baseline of what tests passed/failed prior to an upgrade. ... | 2019-02-18 08:00 | 2019-02-18 17:00 | 1 | 38 | 23-03-2024 00:00 | 23-03-2024 00:00
5.4 | NON-PROD: Schedule upgrade in HI and verify upgrade configurations | Schedule the non-production upgrade in HI and verify your upgrade configurations. | 2019-03-04 08:00 | 2019-03-04 17:00 | 1 | 38,39 | 24-03-2024 00:00 | 24-03-2024 00:00
5.5 | NON-PROD: Validate that the upgrade is complete. | Validate that the upgrade to your non-production instance is complete. | 2019-03-05 08:00 | 2019-03-05 17:00 | 1 | 40 | 25-03-2024 00:00 | 25-03-2024 00:00
5.6 | NON-PROD: Install any optional plugins that were installed on your development instance. | Install any optional plugins that were installed on your development instance. | 2019-03-06 08:00 | 2019-03-06 17:00 | 1 | 41 | 26-03-2024 00:00 | 26-03-2024 00:00
5.7 | NON-PROD: Install custom applications and post-upgrade fix scripts | Install any custom applications and post-upgrade fix scripts that you need. | 2019-03-07 08:00 | 2019-03-07 17:00 | 1 | 42 | 27-03-2024 00:00 | 27-03-2024 00:00
5.8 | NON-PROD: Install update sets. | Install update sets. | 2019-03-08 08:00 | 2019-03-08 17:00 | 1 | 43 | 28-03-2024 00:00 | 28-03-2024 00:00
5.9 | NON-PROD: After upgrade, run Automated Tests | After executing the upgrade, Automated tests should be run again and compared against the pre-upgrade baseline to understand what impact the upgrade may have had on functionality. | 2019-02-20 08:00 | 2019-02-20 17:00 | 1 | 41,44 | 29-03-2024 00:00 | 29-03-2024 00:00
5.1 | NON-PROD: Perform functional testing and monitor the performance | Perform functional testing and monitor the performance of your instance. | 2019-03-11 08:00 | 2019-03-22 17:00 | 10 | 44 | 29-03-2024 00:00 | 2024-11-04
6 | Phase 6 - Prepare to upgrade the production instance | Phase 6 - Prepare to upgrade the production instance... | 2019-02-27 08:00 | 2019-03-26 17:00 | 20 | 36 | 26-03-2024 00:00 | 22-04-2024 00:00
6.1 | Confirm non-production instance defects have been fixed and validated in update sets. | Confirm sign-off from IT and Business stakeholders that all non-production instance defects have been fixed and validated in update sets. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 | 46 | 2024-12-04 | 2024-12-04
6.2 | Confirm the core team of key stakeholders to verify post-upgrade prod functionality | Confirm the core team of key stakeholders required to validate functionality in the ServiceNow instance after the production upgrade. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 | 17 | 2024-12-03 | 2024-12-03
6.3 | Confirm coverage for Day 1 support post-upgrade. | Confirm coverage for Day 1 support post-upgrade. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 | 17 | 13-04-2024 00:00 | 13-04-2024 00:00
6.4 | Create a Production Upgrade Implementation Plan | Create a Production Upgrade Implementation Plan that includes all upgrade steps, roles and responsibilities, communication plans, key contacts, support coverage for Day 1, and so forth. | 2019-02-27 08:00 | 2019-02-27 17:00 | 1 | 48,17 | 13-04-2024 00:00 | 13-04-2024 00:00
6.5 | Schedule Implementation Plan walkthrough and sign-off | Schedule a walkthrough and sign-off of the Implementation Plan with key stakeholders and the core team. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 | 51 | 14-04-2024 00:00 | 14-04-2024 00:00
6.6 | Submit and obtain approvals for change records | Submit and obtain approvals for change records as required by the organization change process. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 | 51 | 14-04-2024 00:00 | 14-04-2024 00:00
6.7 | Send upgrade communications to key stakeholders and end users for production outage and new features | Send a communication to key stakeholders and end users with details for the production upgrade outage, new features, and so forth. | 2019-03-26 08:00 | 2019-03-26 17:00 | 1 | 53,52 | 15-04-2024 00:00 | 15-04-2024 00:00
6.8 | Profile the performance of your instance before upgrading | Profile the performance of your instance before upgrading. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 |  | 26-03-2024 00:00 | 26-03-2024 00:00
6.9 | Use the ServiceNow Performance homepage to document the performance of your instance before the upgrade | Use the ServiceNow Performance homepage to document the performance of your instance before the upgrade. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 |  | 26-03-2024 00:00 | 26-03-2024 00:00
6.1 | On your clone, perform functional testing and monitor the performance of your instance. | On your clone, perform functional testing and monitor the performance of your instance. | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 | 51 | 14-04-2024 00:00 | 14-04-2024 00:00
6.11 | OPTIONAL: Conduct performance and load testing. | OPTIONAL: If there are concerns with system performance, it may beneficial to conduct performance and load testing, to determine any impact areas or remediation steps. (Recommended load testing products are Jmeter and LoadImpact) | 2019-03-25 08:00 | 2019-03-25 17:00 | 1 |  | 26-03-2024 00:00 | 26-03-2024 00:00
7 | Phase 7 - Upgrade the production instance | Phase 7 - Upgrade the production instance... | 2019-03-27 08:00 | 2019-04-02 17:00 | 5 | 47 | 23-04-2024 00:00 | 29-04-2024 00:00
7.1 | PROD: Schedule the upgrade in HI | Schedule the upgrade in HI. | 2019-03-27 08:00 | 2019-03-27 17:00 | 1 | 57 | 15-04-2024 00:00 | 15-04-2024 00:00
7.2 | PROD: If applicable, request a version entitlement | If applicable, request a version entitlement. | 2019-03-27 08:00 | 2019-03-27 17:00 | 1 |  | 23-04-2024 00:00 | 23-04-2024 00:00
7.3 | PROD: Monitor the upgrade and validate that the upgrade is complete | Monitor the upgrade to your instance and validate that the upgrade to your production instance is complete. | 2019-03-28 08:00 | 2019-03-28 17:00 | 1 | 60 | 16-04-2024 00:00 | 16-04-2024 00:00
7.4 | PROD: Apply update sets and post-upgrade fix scripts | Apply any update sets and post-upgrade fix scripts that you have. | 2019-03-29 08:00 | 2019-03-29 17:00 | 1 | 62 | 17-04-2024 00:00 | 17-04-2024 00:00
7.5 | PROD: User acceptance testing (UAT) | Validate and test your instance by conducting user acceptance testing (UAT). Verify with all key stakeholders that the system is performing properly after production upgrade, and key functionality is available. | 2019-04-01 08:00 | 2019-04-01 17:00 | 1 | 63 | 18-04-2024 00:00 | 18-04-2024 00:00
7.6 | Schedule a Lessons Learned meeting to discuss and document improvements to incorporate into the next ServiceNow upgrade cycle. | Schedule a Lessons Learned meeting to discuss and document improvements to incorporate into the next ServiceNow upgrade cycle.... | 2019-03-27 08:00 | 2019-03-27 17:00 | 1 |  | 23-04-2024 00:00 | 23-04-2024 00:00
7.7 | PROD: Celebrate | Celebrate your new upgrade! | 2019-04-02 08:00 | 2019-04-02 17:00 | 1 | 64 | 24-04-2024 00:00 | 24-04-2024 00:00